## Lead
Employee Payroll Management System
Group Number - 2 (213-Java SL WQ)
Team Lead - Ankit Kumar(2485037)
Frontend Lead- Ankita Chandrakant Patil(2486974)
Backend Lead - Batta Mahendra Chowdary(2486659)

## Status Track
Project Status Check Report Team - 2
Sl no. | Employee ID | Name | Domain | Model | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-28
1 | 2485717 | Amulya Shree N M | Frontend | Admin | Admin Dashboard(Html,CSS) | Admin(Add,update,delete attendance | Add Salary(Html,CSS) | Add Schedule(Html,CSS) | Add Leave(Html,CSS) | Add Leave(ts,service)
2 | 2484889 | Ankireddipalli Vivekanandareddy | Backend | Admin | ER Diagram ,Database | Admin Leave Model,Controller | Admin Leave Service | Admin Leave Repository | Testing | Integration
3 | 2487047 | Arcot Hemanth Rayan | Backend | Admin | ER Diagram ,Database | Admin WorkSchedule Model, Controller | Admin WorkSchedule Service | Admin WorkSchedule Repository | Testing | Integration
4 | 2485037 | Ankit Kumar(TL) | Backend | Admin | ER Diagram ,Database | Admin Attendance Model,Controller | Admin Attendance Service | Admin Attendance Repository | Testing | Integration
5 | 2486974 | Ankita Chandrakant Patil | Frontend | Admin | Home Page(Html,CSS) | Login(Html,CSS),Authentication(Services) | Registration(HTML,CSS) | Employee dashboard(Html,CSS) | Employee(service) | Add Salary(services)
6 | 2485062 | Ankitha A Jain | Backend | Admin | ER Diagram ,Database | AdminSalary Model,Controller | AdminSalaryService | AdminSalaryRepository | Testing | Integration
7 | 2484992 | Ankit Kumar | Backend | Employee | ER Diagram ,Database | Employee Model, Controller | Employee Services | Employee Repository | Testing | Integration
8 | 2485213 | Arvind X | Frontend | Employee | Employee Details(Html, CSS) | Employee Details(ts,service) | View Leave(Html, CSS) | View Leave(ts,service) | View WorkSchdule(Html, CSS) | View WorkSchdule(ts,service)
9 | 2485706 | Balaji Venkatesh | Frontend | Employee | View Attendance (Html,CSS) | View Attendance (ts,service) | View Salary(Html) | View Salary(ts,service) | View User Details(Html,CSS) | View User Details(ts,service)
10 | 2486659 | Batta Mahendra Chowdary | Backend | User | Database | Auth Model,Controller(Log in , sign Up) | AuthService , UserRepository | UserDetails Component , AuthSevice.ts | Testing | Integration

## Status Merting
Status Meeting Group - 213 Java SL WQ Batch - Group 2
Meeting Date | Time | Progress Check | Time | Problem Solving | Time | Collaboration
2020-03-22 | 9:30 | a | 2:30 | a | 6:20 | a
2020-03-23 | 9:30 | a | 1:30 | a | 6:20 | a
2020-03-24 | 9:30 | a | 2:30 | a | 6:10 | a
2020-03-25 | 9:30 | a | 2:00 | a | 6:30 | a
2020-03-26 | 9:30 | a | 1:30 | a | 6:30 | a
2020-03-28 | 9:30 | a | 1:00 | a | 6:30 | a